## 工作表1
Date | Start | Stop | Task | Comments
01/29/2020 | 9:30 | 10:00 | problem | think about topic and advisor
2020-07-02 | 11:30 | 12:20 | problem | search online for our topic
2020-10-02 | 21:00 | 22:00 | problem | make slides for first presentation
02/17/2020 | 11:00 | 12:00 | problem | look up about google speech API
02/17/2020 | 17:00 | 17:20 | meeting | meet with Dr. Hsu (talk about first presentation and decide weekly meeting time
02/17/2020 | 17:40 | 18:20 | problem | update information, main task changed to try using Keras and do research about AWS (may use Amazon Lightsail)
02/28/2020 | 20:00 | 20:30 | problem | search about updated information
2020-01-03 | 17:00 | 18:40 | coding & diagram | make diagrams and write codes for basic functions
2020-02-03 | 17:00 | 17:20 | meeting | weekly meeting with Dr. Hsu
2020-05-03 | 20:00 | 21:00 | problem | do research for AI training
2020-09-03 | 13:00 | 15:00 | problem | do research for AI training and search for datasets
03/13/2020 | 17:00 | 19:00 | problem | prepare for second presentation
03/15/2020 | 20:00 | 21:00 | problem | prepare for second presentation
03/18/2020 | 12:30 | 13:00 | presentation | second presentation
03/22/2020 | 19:30 | 22:00 | problem | install Ubuntu and set Ubuntu settings
03/24/2020 | 18:00 | 22:00 | problem | research about Ubuntu, set environment and download packages
03/25/2020 | 16:00 | 16:30 | problem | research for AI model training
03/26/2020 | 12:00 | 12:20 | problem | make decision on using DeepSpeech2 with Sixiang
03/27/2020 | 17:00 | 22:00 | problem | download all needed packages and tools for DeesSpeech2 and start learning
03/31/2020 | 18:00 | 19:00 | problem | get language model and traning dataset ready
2020-01-04 | 15:00 | 20:00 | problem & coding | training with tiny dataset
2020-03-04 | 18:00 | 20:00 | problem | research about manifest and model application
2020-06-04 | 17:00 | 17:10 | meeting | report by slack
2020-10-04 | 20:00 | 22:00 | problem | get inference of the 100 hours trained data and test with testing function by DeepSpeech
2020-11-04 | 19:00 | 19:40 | coding & problem | tried demo_server and demo_client with DeepSpeech's well trained model
2020-12-04 | 17:00 | 17:30 | meeting | weekly meeting with Dr. Hsu
04/13/2020 | 11:00 | 12:30 | problem | do inference with new trianed model (trained 460 hours), and test with testing function by DeepSpeech
04/14/2020 | 11:00 | 11:30 | problem | research for new datasets
04/17/2020 | 16:00 | 18:00 | coding | try generate local server
04/20/2020 | 19:00 | 21:00 | problem | research for model using
04/21/2020 | 20:00 | 21:30 | problem | learn about Common Voice
04/24/2020 | 11:00 | 13:00 | coding | work with datasets from Common Voice, write function to use .tsv file generating manifest and convert audio type to wav in order to use with DeepSpeech2
04/26/2020 | 13:00 | 16:00 | coding | finish python file for Common Voice, generate manifest
04/28/2020 | 8:00 | 10:00 | coding | combine Common Voice datasets and Libir Speech datasets, write transcript function with trained model
2020-02-05 | 15:30 | 17:30 | coding | do inference by two kinds of datasets (clean voice and unclean voice) with models we trained and compare
2020-06-05 | 17:00 | 19:00 | coding | try to improve transcript function (to be more efficient)
2020-07-05 | 19:00 | 20:00 | problem | make final presentation slides
2020-08-05 | 10:00 | 10:30 | problem | schedule final presentation time
2020-10-05 | 19:00 | 21:00 | coding | check all files, prepare for final presentation
2020-11-05 | 20:00 | 22:00 | problem | make final presentation slides
2020-12-05 | 9:00 | 10:00 | presentation | final presentation